## Test Plan
PROJECT NAME: | BANTAY-TB: Web-Based Tuberculosis Case Surveillance, Hotspot Mapping, and Treatment-Adherence System for Davao City
TEST PLAN ID: | BTB-TP-001 (Rev. 1.0)
CREATED BY: | Jaydee Magkidong — QA Lead, BANTAY-TB Capstone Team
DATE OF CREATION: | October 1, 2026
DATE OF REVIEW: | October 8, 2026
TEST ITEM | TEST STRATEGY | TEST TYPE | FEATURES TO BE TESTED | FEATURES NOT TO BE TESTED | ENTRY CRITERIA | EXIT CRITERIA | DELIVERABLES | START DATE | END DATE | ASSIGNEE | RISK ANALYSIS
TI-01 — Authentication, Staff Registration & Patient Account Claiming | Manual black-box scenario testing per role, paired with Vitest unit tests on the claim/invite helpers; negative-path driven (wrong code, expired code, reused code). | Functional, Security (authorization), Negative | Email/password login (/login); staff self-registration gated by invite code (/register/staff); patient claim-slip flow (/claim, ClaimSlip); forgot/reset password; invite-code issuance and single-use consumption (/app/invites); patient-code generation (/app/patient-codes); session persistence and logout; redirect of unauthenticated users. | Supabase Auth internals (token signing, email delivery infrastructure); third-party SMTP deliverability; OAuth/social login (not implemented). | Staging Supabase project migrated to the latest migration; at least one system_admin and one tb_coordinator seeded; invite-code and patient-code tables reachable; npm run dev serves without console errors. | All High-severity auth cases pass; no invite or patient code can be redeemed twice; no self-registration path grants a privileged role without a valid code; zero open Critical/High defects. | Test cases TC-01-01…TC-01-14; executed test log; defect report; screenshots of each flow; Vitest run output. | Oct 6, 2026 | Oct 9, 2026 | Member 1 (QA Lead) | High. A flaw here exposes patient records. Roles are assigned by the claim/invite flow — not by the registration form — so any gap lets a user mint their own privileges. Residual risk: password-reset emails cannot be fully verified on the free tier; mitigated by testing the token path directly.
TI-02 — Role-Based Access Control & Area/Facility Scoping (RLS) | Permission-matrix testing — each of the five roles (system_admin, tb_coordinator, barangay_admin, health_worker, patient) is driven against every guarded route and table; backed by areaScope.test.ts and caseAttribution.test.ts. | Security, Functional, Integration (database policy) | RequireRole route guards on all 17 app routes; RLS policies on cases, adherence_schedules, hotspots, alerts, profiles; residence (barangay_psgc) versus treatment-facility (facility_id) scoping; a patient seeing only their own records; citywide read for coordinators versus barangay-only read for barangay admins and BHWs; direct-URL access attempts and API calls that bypass the UI. | PostgreSQL's own policy engine; service-role key behavior (server-side only); penetration testing of the hosting platform. | TI-01 passed; one test account per role seeded across at least two barangays and two DOTS facilities; permission matrix reviewed and signed off. | Every cell of the permission matrix matches the specification; no cross-barangay or cross-facility record leaks through the UI or a direct Supabase query; all guarded routes redirect unauthorized roles. | Role × route × table permission matrix (filled); negative-access evidence log; RLS test queries; defect report. | Oct 9, 2026 | Oct 14, 2026 | Member 1 (QA Lead) with Member 4 (Back-End/DB) | Critical. The highest-risk item in the plan — a leak is both a privacy breach and a Data Privacy Act compliance failure. Residence and treatment facility are two independent axes, so scoping bugs are easy to introduce and hard to see; demo facility links are synthetic backfill, which can mask a real-world mismatch. Mitigated by testing at the database layer, not only through the UI.
TI-03 — Case Filing, Case List & Case Management | Equivalence partitioning and boundary analysis on the case form, plus CRUD lifecycle walkthroughs per role; caseFiling.test.ts and facilityFlows.test.ts as the unit safety net. | Functional, Data validation, Regression | New case filing (/app/cases/new); required-field and format validation (age, sex, diagnosis date, TB site, diagnosis status, treatment outcome); residence address capture and barangay resolution; DOTS treatment-facility assignment; case list filtering, search, and pagination (/app/cases); PatientSheet detail view; edit and status transitions; realtime case updates; audit of who filed each case. | Deletion of historical cases (intentionally restricted); DOH ITIS integration (out of scope); printed clinical forms. | TI-02 passed; barangay PSGC reference data and DOTS centers loaded (dots_centers_davao.sql); case-form field specification final. | No invalid case can be saved; every saved case carries the correct residence barangay, facility, and filer attribution; filters and search return correct result sets; status transitions follow the allowed sequence. | Test cases TC-03-01…TC-03-22; boundary-value table; executed log with screenshots; defect report. | Oct 12, 2026 | Oct 17, 2026 | Member 2 (Front-End) | High. Case records feed the map, the hotspot engine, and every chart downstream, so a validation gap propagates silently. Diagnosis status must stay distinct from treatment outcome — conflating them corrupts the surveillance picture. Mitigated by validating at both the form layer (Zod) and the database layer.
TI-04 — Bulk Excel Import & Data Migration | File-based destructive and non-destructive testing with crafted workbooks — valid, partially invalid, wrong headers, duplicate rows, empty file, oversized file; importScope.test.ts as the scope guard. | Functional, Data integrity, Negative, Boundary | Excel upload and parsing (/app/import, SheetJS); header and column mapping; per-row validation with a reviewable error report; append-only behavior for BHW/nurse/doctor imports, including automatic stamping of the importer's assignment; coordinator-only replace-all import; duplicate detection; import audit trail and stored file in the excel_imports bucket; rollback on failure. | Microsoft Excel itself; CSV and Google Sheets import (not supported); imports above the documented row ceiling. | TI-03 passed; dummy_tb_cases.xlsx plus five crafted negative-case workbooks prepared; storage-bucket migration applied. | No malformed row is ever persisted; a field-role import can only add records, never replace existing ones; replace-all is reachable only by a coordinator; row counts reconcile exactly before and after each import. | Test workbook set (valid plus five negative); import reconciliation sheet; error-report screenshots; defect report. | Oct 15, 2026 | Oct 20, 2026 | Member 2 (Front-End) with Member 4 (Back-End/DB) | High. The replace-all path can destroy existing records, so it must be provably coordinator-only; an append-only role that gains replace rights is a data-loss defect, not merely a permission defect. Residual risk: real DOH workbooks may use column layouts the team has not seen — mitigated by testing against the actual facility-supplied template.
TI-05 — GIS Mapping & Geospatial Resolution | Exploratory testing with visual verification against known Davao City coordinates; unit tests in nearestBarangay.test.ts; cross-browser map rendering checks. | Functional, Usability, Compatibility, Performance | Case map rendering (/app/map, AdminHotspotMap, MapLibre/OpenFreeMap basemap); barangay boundary overlay; heatmap layer (leaflet.heat); marker clustering and popups; address-to-barangay resolution with nearest-barangay fallback (barangayResolver.ts, geocode.ts); public case map (PublicCaseMap) showing aggregated, non-identifying counts; DOTS facility locator (/dots-locator) with device geolocation; zoom, pan, and layer toggles. | Accuracy of third-party basemap tiles and the geocoder; GPS hardware precision; offline map caching. | TI-03 passed; barangay GeoJSON boundaries and DOTS center coordinates loaded; at least 150 seeded cases spread across 10 or more barangays; map tile endpoint reachable. | Every seeded case plots in its correct barangay; boundaries align with plotted points; the public map exposes no individual-level location; the map is interactive within 3 seconds on the target build; renders correctly in Chrome, Edge, and Firefox. | Geocoding accuracy spot-check table (30 addresses); annotated map screenshots per layer; browser compatibility matrix; defect report. | Oct 19, 2026 | Oct 24, 2026 | Member 3 (GIS/Analytics) | Medium-High. A mis-resolved address moves a case into the wrong barangay and quietly skews hotspot output. Patient privacy is at stake on the public map, where only aggregates may appear. Residual risk: tile and geocode provider rate limits during the demo — mitigated by a cached fallback basemap.
TI-06 — Hotspot Detection (DBSCAN) & Alert Generation | Algorithm testing against hand-computed expected clusters on fixed synthetic datasets; parameter sweeps over ε and minPts; dbscan.test.ts, hotspotAlerts.test.ts, hotspotRefresh.test.ts. | Functional, Algorithmic correctness, Integration (Edge Function), Performance | DBSCAN clustering (dbscan.ts) with configurable settings (dbscanSettings.ts); detect-hotspots Edge Function invocation and scheduled refresh; hotspot persistence and recomputation idempotency; hotspot list and detail (/app/hotspots); alert creation, acknowledgement, and resolution (/app/alerts); residence barangay carried onto each alert; hotspot deletion policy. | Epidemiological validity of the chosen ε/minPts for declaring a real outbreak (clinical judgment, not software); predictive forecasting (not implemented). | TI-05 passed; three fixed synthetic datasets with hand-computed cluster assignments prepared; Edge Function deployed to staging; baseline parameters documented. | Algorithm output matches the hand-computed clusters for all three datasets; no duplicate hotspots after repeated refresh; every hotspot raises exactly one alert carrying the correct residence barangay; a refresh over 1,000 cases completes within the documented time budget. | Expected-versus-actual cluster comparison sheet; parameter-sensitivity table; Edge Function logs; defect report. | Oct 22, 2026 | Oct 28, 2026 | Member 3 (GIS/Analytics) | High. A false negative hides a real cluster from health workers; a false positive wastes scarce field resources. Output is only as good as TI-05's geocoding, so defects can originate upstream. Residual risk: no ground-truth outbreak data is available for validation — mitigated by synthetic datasets with known answers plus adviser review of the parameters.
TI-07 — Treatment-Adherence Scheduling & SMS Reminder Pipeline | End-to-end pipeline tracing (schedule → dose fan-out → Edge Function → provider → audit row) with the SMS provider in sandbox mode; state-transition testing of dose status; enrollment.test.ts and reminders.test.ts. | Functional, Integration (third-party), State-transition, Negative | Patient enrollment (EnrollPatientPanel); schedule creation on /app/adherence (medication, dose, frequency, start and end date); auto-generated per-dose rows in adherence_logs; dose status transitions (scheduled → taken / missed / late); the hourly send-adherence-sms function picking up doses due within the hour; localized SMS body (en/tl/ceb); sms_outbox audit rows; overdue sweep marking doses missed; the patient-side adherence view; RLS confining schedules to the patient and their barangay staff. | Actual telco delivery latency and carrier filtering; provider billing; per-dose confirmation SMS and proof-of-intake capture (excluded by the August 2026 design rulings); patient self-registration (not permitted). | TI-02 passed; SMS provider sandbox credentials configured; cron trigger enabled on staging; one enrolled test patient with a reachable sandbox number. | Dose rows generate correctly for daily and weekly regimens including the end-date boundary; exactly one SMS per due dose with no duplicates across repeated function runs; message language matches the patient's preference; every dispatch has a matching sms_outbox row; overdue doses flip to missed on schedule. | Pipeline trace log (one dose, end to end); dose state-transition diagram with results; sandbox SMS screenshots; sms_outbox reconciliation extract; defect report. | Oct 26, 2026 | Nov 2, 2026 | Member 4 (Back-End/DB) | High. Duplicate or missed reminders directly affect treatment adherence, and a sent SMS cannot be recalled. The feature depends on an external provider the team does not control. Residual risk: cron timing and time-zone handling (Asia/Manila) are hard to verify inside a short test window — mitigated by manual function invocation with injected clock values and by keeping the provider in sandbox mode until UAT.
TI-08 — Clinical Decision Support, Health Education & Chatbot | Scenario-based testing with clinically reviewed input sets; content review against DOH NTP material; articleBlocks.test.ts for content rendering. | Functional, Content accuracy, Usability | CDS screening and recommendation output (/app/cds, health-worker only); symptom infographic and icon rendering (SymptomInfographic, SymptomIcon); health-education articles for the eight respiratory conditions bundled in src/ (TB, COPD, asthma, bronchitis, pneumonia, influenza, COVID-19, paragonimiasis); patient education view (/app/education); public learn page (/learn); chatbot Edge Function responses in-app (/app/chatbot) and on the public FAB (PublicChatbotFab); refusal and escalation behavior on out-of-scope or emergency questions. | Diagnostic accuracy as a medical device (the tool is advisory only); the language-model provider's internals; content in languages beyond the three supported. | TI-01 passed; chatbot Edge Function deployed with a working key; adviser or clinical reviewer available for content sign-off; 20 scripted patient questions prepared, including five emergency and five out-of-scope prompts. | CDS recommendations match the reviewed rule table for all scripted cases; all eight condition articles render completely in all three languages; the chatbot never gives a definitive diagnosis and escalates every emergency prompt to seek-care-immediately guidance; the clinical reviewer signs off on the content. | CDS input/expected-output rule table; chatbot transcript log (20 prompts); content review sign-off sheet; defect report. | Oct 30, 2026 | Nov 5, 2026 | Member 5 (Content/UX) with the clinical reviewer | High (safety rather than technical). Wrong clinical content can cause real harm and is the most likely source of panel objections. A chatbot that sounds authoritative is more dangerous than one that defers. Mitigated by mandatory human review of every recommendation string and by explicit refusal testing.
TI-09 — Analytics, Dashboards & Reporting | Data-driven verification — every chart figure recomputed independently in SQL against the same seeded dataset, then cross-checked across dashboards for consistency. | Functional, Data accuracy, Regression | Role dashboards (/app/dashboard, /app/admin); analytics charts and trends (/app/analytics); case counts by barangay, facility, TB site, diagnosis status, and treatment outcome; ACF (active case finding) presumptive-screening yield reported separately from active cases on treatment; period filters and date ranges; empty-state and single-record states; export of report figures; DotsCentersAdmin and Users admin tables. | Statistical significance testing; official DOH report-form generation; historical data prior to the seeded period. | TI-03 and TI-04 passed; frozen seeded dataset with independently known totals; indicator definitions documented and agreed. | Every displayed figure matches its independently computed SQL value exactly; the same indicator agrees across all dashboards; presumptive and active-case counts are never summed into one total; empty states render without errors. | Chart-versus-SQL reconciliation workbook; indicator definition sheet; dashboard screenshots per role; defect report. | Nov 2, 2026 | Nov 7, 2026 | Member 3 (GIS/Analytics) | Medium-High. ACF screening yield counts symptomatic/presumptive individuals, not confirmed cases — adding it to active cases on treatment inflates the numbers and is the single most likely reporting defect. Dashboards are also what the panel looks at first, so a visible inconsistency costs credibility. Mitigated by independent recomputation rather than eyeballing.
TI-10 — Public Site, Trilingual Support & Cross-Device Usability | Checklist-based UI/UX review on real devices, plus automated i18n key-coverage checks (i18n.test.ts) and an informal usability session with five non-technical participants. | Usability, Compatibility, Accessibility, Localization, Responsive | Public landing, about, learn, and DOTS locator pages; navigation and page transitions; language switching across English, Filipino (Tagalog), and Cebuano with no missing or untranslated keys; text expansion without layout breakage; responsive layout at 360px, 768px, and 1280px widths; keyboard navigation, focus order, form labels, and color contrast; toast and error message clarity; loading and lazy-fallback states. | Full WCAG 2.1 AA certification; screen-reader support beyond basic landmark and label checks; browsers older than the two most recent major versions; native mobile apps. | TI-01 through TI-09 feature-complete on the staging build; translation files complete for all three languages; test devices available (one Android phone, one tablet, one laptop); five usability participants recruited. | No untranslated or missing key in any language; no horizontal scroll or clipped text at any tested width; all interactive controls reachable by keyboard; contrast ratios meet 4.5:1 for body text; participants complete the three core tasks unaided; zero open High usability defects. | Device and browser compatibility matrix; i18n coverage report; usability session notes with task success rates and SUS scores; annotated screenshots; defect report. | Nov 5, 2026 | Nov 11, 2026 | Member 5 (Content/UX) | Medium. BHWs and patients are the real users, many on low-end Android phones over mobile data, so a desktop-only pass is not evidence. Cebuano and Tagalog strings are the likeliest to be stale because they are translated last; the files are UTF-8, and a careless tooling round-trip corrupts the trilingual content. Mitigated by automated key-coverage tests and native-speaker review.
TI-11 — Regression, Build Integrity & Deployment Readiness | Automated regression suite on every build (npm run lint, npm run typecheck, npm run test), followed by a scripted smoke walkthrough of all five roles on the deployed Firebase build. | Regression, Smoke, Build verification, Non-functional (performance, security configuration) | Full Vitest suite (13 test files) green; zero TypeScript and ESLint errors; production build succeeds and the bundle loads; lazy-loaded route chunks resolve; environment variables and keys absent from the client bundle; Firebase Hosting deployment and SPA route rewrites; migrations applying cleanly from an empty database; first-load performance on a throttled 3G profile; graceful behavior when Supabase is unreachable. | Load and stress testing beyond the demo-scale dataset; disaster recovery and backup restoration; formal penetration testing; CI pipeline configuration (builds are manual for this project). | TI-01 through TI-10 executed with no open Critical or High defects; release candidate tagged; migration chain verified in order; deployment checklist prepared. | All automated checks pass on the release candidate; the smoke walkthrough passes for all five roles on the deployed URL; no secret or service-role key appears in the client bundle; first contentful paint under 3 seconds on the throttled profile; final test summary report signed by the adviser. | Automated test run output; regression checklist; deployment verification log; bundle secret-scan result; final Test Summary Report and defect-closure log. | Nov 9, 2026 | Nov 14, 2026 | Member 1 (QA Lead) with the full team | Medium-High. This is the last gate before defense, so schedule pressure makes it the item most likely to be cut short — the automated suite partly protects against that. The most damaging possible defect is an exposed key in the client bundle, hence the explicit scan. Residual risk: the demo environment differs from a real DOH deployment; this is stated as a limitation in the final report.